## CivicBudget
CIVICLINK — CITIZEN REQUESTS & COMPLAINTS PLATFORM
Workshop: Lean (post agile) Planning and Budgeting Strategies
Institution | Escuela Colombiana de Ingeniería Julio Garavito (ECI)
Course | Enterprise Architectures
Team | Andersson D. Sánchez M. · Cristian S. Pedraza R. · Raquel I. Selma A.
GitHub | https://github.com/AnderssonProgramming/civic-requests-platform
ESTIMATION METHOD
Formula | Budget = Cost per Sprint × Number of Sprints + Tools + Equipment + Contingency
Sprints formula | ⌈ Total SP / Velocity ⌉ = ⌈218 / 45⌉ = 5 sprints
Estimation technique | Planning Poker — Fibonacci scale (1, 2, 3, 5, 8, 13)
EXECUTIVE SUMMARY
Metric | Value | Notes
Total Backlog (SP) | 218 | 9 epics, 51 user stories
Sprint Length | 2 weeks | 10 working days per sprint
Steady-state Velocity | 45 SP / sprint | Industry benchmark, steady from Sprint 2
Number of Sprints | 5 | ⌈218 / 45⌉ = 5 + 1-week Sprint 0
Project Duration | 11 weeks | Sprint 0 (1w) + 5 sprints (10w)
Total Team Hours | 3160 | 7 roles, mixed allocations
Labor Cost (USD) | 124600 | Fully loaded rates
Tools & Licenses (USD) | 4650 | Dev + staging environments
Equipment & Onboarding (USD) | 2000 | Hardware, training, kickoff
Contingency 15% (USD) | 19688 | 15% of subtotal
TOTAL ESTIMATE P50 (USD) | 150938 | Point estimate
Optimistic P10 (USD) | 128300 | −15% on total
Pessimistic P90 (USD) | 173580 | +15% on total
COP Equivalent (@ 4,200) | ~ COP 633,940,000 | Indicative rate April 2026
Cost per Story Point (USD) | ~$692 | Fully loaded — use for change-request pricing
LABOR COST BREAKDOWN
Role | Allocation | Total Hours | Rate (USD/h) | Cost (USD) | Cost (COP @ 4,200) | Notes
Project Manager | 0.6 | 240 | 40 | 9600 | COP 40,320,000 | Fully loaded rate
Tech Lead / Solution Architect | 1 | 400 | 60 | 24000 | COP 100,800,000 | Fully loaded rate
Frontend Developer #1 | 1 | 400 | 35 | 14000 | COP 58,800,000 | Fully loaded rate
Frontend Developer #2 | 1 | 400 | 35 | 14000 | COP 58,800,000 | Fully loaded rate
Backend Developer #1 | 1 | 400 | 38 | 15200 | COP 63,840,000 | Fully loaded rate
Backend Developer #2 | 1 | 400 | 38 | 15200 | COP 63,840,000 | Fully loaded rate
DevOps Engineer | 0.8 | 320 | 45 | 14400 | COP 60,480,000 | Fully loaded rate
QA Engineer | 1 | 400 | 28 | 11200 | COP 47,040,000 | Fully loaded rate
UX/UI Designer | 0.5 | 200 | 35 | 7000 | COP 29,400,000 | Fully loaded rate
TOTAL LABOR |  | 3160 |  | 124600 | COP 523,320,000
ASSUMPTIONS
Rates are blended mid+senior, fully loaded (gross salary + ~40% employer social contributions + overhead).
Hours = 80 hrs/sprint × 5 sprints × allocation. Sprint 0 (1 week) absorbed within totals.
No overtime. A 6th sprint would add ~$24,920 labor at the same team composition.
Rates reflect the Colombian software-development market, Bogotá, April 2026.
TOOLS & LICENSES (10 weeks)
Item | Tier / Notes | Cost (USD) | Cost (COP)
GitHub Team (9 seats) | Team | 200 | COP 840,000
Auth0 Essentials | Up to 1k MAU | 500 | COP 2,100,000
Atlassian Jira + Confluence | 10 seats | 300 | COP 1,260,000
Figma | 3 editor seats | 150 | COP 630,000
Sentry Team | 1 organization | 300 | COP 1,260,000
Datadog / Grafana Cloud Pro | 5 hosts | 500 | COP 2,100,000
AWS dev + staging (compute, RDS, S3, MSK, CloudWatch) | Mixed | 2500 | COP 10,500,000
Domains, SSL, miscellaneous | — | 200 | COP 840,000
Subtotal Tools |  | 4650 | COP 19,530,000
EQUIPMENT & ONBOARDING
Item | Notes | Cost (USD) | Cost (COP)
Hardware top-up / peripherals (3 × $500) | One-time | 1500 | COP 6,300,000
Onboarding, training material, kickoff workshop | One-time | 500 | COP 2,100,000
Subtotal Equipment |  | 2000 | COP 8,400,000
BUDGET ROLL-UP
Category | USD | COP
Labor | 124600 | COP 523,320,000
Tools & Licenses | 4650 | COP 19,530,000
Equipment & Onboarding | 2000 | COP 8,400,000
Subtotal | 131250 | COP 551,250,000
Contingency (15%) | 19688 | COP 82,689,600
TOTAL (P50) | 150938 | COP 633,939,600
Optimistic P10 | 128297 | COP 538,847,400
Pessimistic P90 | 173579 | COP 729,031,800
AGILE PRODUCT BACKLOG — EPIC SUMMARY
ID | Epic Name | Stories | Story Points | MoSCoW | Sprints
E1 | Citizen Onboarding & Authentication | 6 | 21 | Must | 1
E2 | Request Submission | 8 | 34 | Must | 1–2
E3 | Request Tracking | 6 | 21 | Must | 1–3
E4 | Communication | 4 | 16 | Should | 3
E5 | Admin Operations | 8 | 39 | Must | 4
E6 | Reports & Analytics | 5 | 26 | Should | 5
E7 | Notifications | 4 | 16 | Should | 3–4
E8 | Integrations | 4 | 21 | Could | 5+
E9 | Platform & Quality (NFR) | 6 | 24 | Must | 1–5
TOTAL |  | 51 | 218
DETAILED USER STORIES
ID | User Story | SP | MoSCoW | Epic | Sprint
US-01 | As a citizen, I want to register an account with email and password so that I can submit and track requests. | 5 | Must | E1 | 1
US-02 | As a citizen, I want to log in with email/password so that I can access my dashboard. | 3 | Must | E1 | 1
US-03 | As a citizen, I want to log in with Google so that I avoid creating yet another password. | 5 | Must | E1 | 1
US-04 | As a citizen, I want to recover my password by email so that I can regain access if I forget it. | 3 | Must | E1 | 1
US-05 | As a citizen, I want to edit my profile (name, phone, address) so that the city has accurate contact info. | 3 | Must | E1 | 4
US-06 | As a citizen, I want to verify my email so that my account is trustworthy. | 2 | Must | E1 | 1
US-07 | As a citizen, I want to submit a request with a title and description so that the city knows what to fix. | 5 | Must | E2 | 1
US-08 | As a citizen, I want to pick a category (lighting, waste, infrastructure, noise, other) so that the right department gets it. | 3 | Must | E2 | 1
US-09 | As a citizen, I want to attach up to 5 photos so that staff see the actual issue. | 5 | Must | E2 | 2
US-10 | As a citizen, I want to pin the location on a map so that staff find it quickly. | 8 | Must | E2 | 2
US-11 | As a citizen, I want to submit anonymously for sensitive issues so that I'm not exposed. | 5 | Should | E2 | 2
US-12 | As a citizen, I want to save a draft so that I can finish later. | 3 | Should | E2 | 2
US-13 | As a citizen, I want inline form validation so that I know what's missing before I submit. | 2 | Must | E2 | 1
US-14 | As a citizen, I want a tracking ID receipt (e.g. PQRS-2026-00042) so that I can follow up without an account. | 3 | Must | E2 | 1
US-15 | As a citizen, I want to see all my requests in a list so that I have one place to look. | 3 | Must | E3 | 2
US-16 | As a citizen, I want to see the current status of each request so that I know where it stands. | 3 | Must | E3 | 2
US-17 | As a citizen, I want to view the full timeline of a request so that I see every step taken. | 5 | Must | E3 | 3
US-18 | As a citizen, I want to see which department and staff member is handling my case. | 2 | Should | E3 | 4
US-19 | As a citizen, I want to track a request via a public link with the tracking ID so that I don't always need to log in. | 5 | Must | E3 | 2
US-20 | As a citizen, I want to filter and search my requests so that I find the one I care about. | 3 | Should | E3 | 2
US-21 | As a citizen, I want to send messages to staff about my request so that I can clarify or add info. | 5 | Should | E4 | 3
US-22 | As staff, I want to reply to citizens through the platform so that conversation history is preserved. | 5 | Should | E4 | 3
US-23 | As a citizen, I want to be alerted when staff replies so that I respond promptly. | 3 | Should | E4 | 3
US-24 | As a citizen, I want to rate the resolution after closing so that the city improves. | 3 | Should | E4 | 5
US-25 | As an admin, I want a dashboard listing all open requests so that I see the full operational load. | 5 | Must | E5 | 1
US-26 | As an admin, I want to filter by department, urgency, location, and status. | 5 | Must | E5 | 2
US-27 | As a department head, I want to assign requests to specific staff so that work is distributed fairly. | 8 | Must | E5 | 4
US-28 | As staff, I want to update the status of my requests so that citizens see progress. | 3 | Must | E5 | 4
US-29 | As staff, I want to add internal notes invisible to citizens so that the team coordinates. | 3 | Must | E5 | 4
US-30 | As an admin, I want overdue requests automatically escalated so that nothing rots silently. | 5 | Must | E5 | 4
US-31 | As an admin, I want to manage department configurations so that the org evolves without code changes. | 5 | Must | E5 | 4
US-32 | As an admin, I want to manage roles and permissions so that access matches responsibility. | 5 | Must | E5 | 4
US-33 | As an admin, I want a KPI dashboard (open requests, avg resolution time, SLA compliance, satisfaction). | 8 | Should | E6 | 5
US-34 | As an admin, I want per-department performance reports so that I identify bottlenecks. | 5 | Should | E6 | 5
US-35 | As an admin, I want request distribution maps and charts by category and zone. | 5 | Should | E6 | 5
US-36 | As an admin, I want to export reports to PDF and Excel so that I share with the council. | 3 | Should | E6 | 5
US-37 | As a citizen/journalist, I want a public transparency dashboard so that the city is held accountable. | 5 | Should | E6 | 5
US-38 | As a citizen, I want email notifications on every status change so that I'm informed. | 5 | Should | E7 | 3
US-39 | As a citizen, I want SMS notifications for urgent updates so that I don't miss them. | 5 | Should | E7 | 3
US-40 | As a citizen, I want in-app notifications so that I see updates next time I open the portal. | 3 | Should | E7 | 3
US-41 | As a citizen, I want to manage notification preferences so that I'm not spammed. | 3 | Should | E7 | 4
US-42 | As a citizen, I want to log in with Carpeta Ciudadana Digital (Colombian government SSO). | 8 | Could | E8 | 5+
US-43 | As an admin, I want the platform to consume the municipal GIS layer of public lighting. | 5 | Could | E8 | 5+
US-44 | As a journalist/developer, I want a public REST API so that open data is consumable. | 5 | Could | E8 | 5+
US-45 | As an admin, I want outbound webhooks to external contractors so that partners are auto-notified. | 3 | Could | E8 | 5+
US-46 | As DevOps, I want CI/CD pipelines per service so that deployments are automated and auditable. | 5 | Must | E9 | 1
US-47 | As DevOps, I want centralised metrics, logs, and traces so that incidents are diagnosable. | 5 | Must | E9 | 5
US-48 | As a security officer, I want OWASP Top-10 mitigations and dependency scanning. | 5 | Must | E9 | 1–5
US-49 | As a developer, I want feature flags so that risky changes ship safely. | 3 | Should | E9 | 4
US-50 | As a citizen, I want a fully mobile-friendly PWA so that I use the platform from any phone. | 3 | Must | E9 | 1
US-51 | As an accessibility advocate, I want WCAG 2.1 AA compliance so that every citizen is included. | 3 | Must | E9 | 5
TOTAL |  | 218
SPRINT PLAN & VELOCITY MODEL | Story Points | Cumulative SP | Focus / Deliverable | Cost (USD) | Cost (COP)
Sprint | 0 | 0 | Repo, CI/CD, Auth0 tenant, environments, design system | 5000 | COP 21,000,000
Sprint 0 (Setup, 1w) | 45 | 45 | Auth, profile, base submission, API gateway, CI pipelines | 30188 | COP 126,789,600
Sprint 1 | 47 | 92 | Photos, geolocation, drafts, validations, tracking ID | 30188 | COP 126,789,600
Sprint 2 | 45 | 137 | Tracking timeline, citizen-staff messaging, notifications | 30188 | COP 126,789,600
Sprint 3 | 43 | 180 | Admin dashboard, assignment, escalation, roles, departments | 30188 | COP 126,789,600
Sprint 4 | 38 | 218 | KPIs, reports, open-data API, NFR polish, UAT | 30188 | COP 126,789,600
Sprint 5
VELOCITY NOTES
⌈218 SP / 45 velocity⌉ = 5 sprints. Sprint 0 is setup only (1 week, no committed SP).
If velocity drops to 35 SP the plan needs 7 sprints → ~+$60k, within the P90 range.
Could epic (E8, 21 SP) is not committed — pulled in if Sprint 5 has leftover capacity.
RISK REGISTER (COST-RELEVANT)
ID | Risk Description | Likelihood | Max Impact (USD) | Mitigation
R1 | Carpeta Ciudadana integration delayed or requires paid tier | Medium | 8000 | Treated as Could; buffered in Sprint 5
R2 | Velocity dips below 35 SP for 2+ sprints | Medium | 25000 | 15% contingency + scope re-prioritisation
R3 | Senior developer leaves mid-project | Low | 10000 | Tech Lead absorbs; potential +1 sprint
R4 | Cloud cost spike during load tests | Low | 2000 | Rate-limit load tests, schedule off-hours
R5 | Auth0 needs Professional plan earlier than expected | Low | 1500 | Cap MAUs; switch tier if needed
R6 | Currency volatility COP / USD | Medium | — | Lock local contracts in COP; budget in USD
R7 | Scope creep from municipal stakeholders | High | 15000 | MoSCoW + change requests priced at ~$670/SP
CONTINGENCY RATIONALE
15% contingency covers the top 3 risks (R1, R2, R7) at expected-value weighted impact.
Risk R2 (velocity dip) alone could cost $25k but is offset by scope re-prioritisation before spending more.
Risk R7 (scope creep) is managed by MoSCoW — any new story is priced at ~$692/SP before it enters the backlog.